## Feuil1
Work Plan ENTRINGER Gilles | [6 empty] | Calendar
Number | Task | Duration | Date Start | Date End | Location | Collaboration | 2012 |  |  | 2013 | [11 empty] | 2014 | [11 empty] | 2015
[7 empty] | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
WP1 | State of Art and expression of the needs / Data base construction | 6 months | 2012-10-01 | 2013-03-31 | UMR Espece-Dev
1.1 | Bibliography - Expression of the needs
1.1.1 | Bibliography / State of Art (Existant warning systems) | 4 months | 2012-10-01 | 2013-01-31 | UMR Espece-Dev | bar: 2012 10 to 2013 1
1.1.2 | Bibliography / Spatiotemporal indicators | 4 months | 2013-04-01 | 2013-07-31 | UMR Espece-Dev | bar: 2013 4 to 2013 7
1.2 | Data collection | 3 months | 2013-01-01 | 2013-03-31 | UMR Espece-Dev | bar: 2013 1 to 2013 3
1.2.1 | Conceptualisation of a data base | bar: 2013 1 to 2013 3
1.2.2 | Coherence test of the data base | bar: 2013 1 to 2013 3
WP 2 | Indicators | 10 months | 2013-04-01 | 2014-01-31 | UMR Espece-Dev | bar: 2013 4 to 2014 1
2.1.1 | Desciption of knowledge | 4 months | 2013-06-01 | 2013-09-30 | UMR Espece-Dev | bar: 2013 6 to 2013 9
2.2 | Defintion of spatiotemporal indicators | 6 months | 2013-08-01 | 2014-01-31 | UMR Espece-Dev | bar: 2013 8 to 2014 1
WP3 | Development of an automated computer system | 2 months | 2014-02-01 | 2014-03-31 | UMR Espece-Dev | bar: 2014 2 to 2014 3
3.1 | Choise of data based on the indicators | 2 months | 2014-02-01 | 2014-03-31 | UMR Espece-Dev | bar: 2014 2 to 2014 3
3.2 | Evaluation of data / data quality | 2 months | 2014-02-01 | 2014-03-31 | UMR Espece-Dev | bar: 2014 2 to 2014 3
WP4 | Dissemination | 3 months | 2014-04-01 | 2014-06-30 | UMR Espece-Dev | bar: 2014 4 to 2014 6
4.1 | Construction of models of indicators | 2 months | 2014-05-01 | 2014-05-31 | UMR Espece-Dev | bar: 2014 4 to 2014 5
4.2 | Evaluation and validation of models | 1 moth | 2014-06-01 | 2014-06-30 | UMR Espece-Dev | bar: 2014 6
5 | Development of an automated computer system | 14 months | 2014-07-01 | 2015-08-30 | UMR Espece-Dev | bar: 2014 7 to 2015 8
5.2 | Choise of computer architecture | 2 moths | 2014-07-01 | 2014-08-31 | UMR Espece-Dev | bar: 2014 7 to 2014 8
5.3 | Informatic development | 12 months | 2015-01-01 | 2015-08-30 | UMR Espece-Dev | bar: 2014 9 to 2015 8
5.4 | Implementation / Test | 2 months | 2015-07-01 | 2015-08-30 | UMR Espece-Dev | bar: 2015 7 to 2015 8
WP1 Data base construction/
WP2 Indicators
WP3 Development system
WP4 Dissemination
Milestone: 5-6
Articles, Base de données, Modèle indicateurs, Système fonctionnant,
2015:00
8+9 dernier article
Ete: rendu thèse

## Feuil2
Work Plan |  | Calendar
Number | Task | 1-4 | 5-8 | 9-12 | 13-16 | 17-20 | 21-24 | 25-28 | 29-32 | 33-36
WP1 | Bibliography and database construction
1.1 | Bibliography - Expression of the needs
1.1.1 | Bibliography / State of Art (Existant warning systems)
1.1.2 | Bibliography / Spatiotemporal indicators
1.2 | Data collection
1.2.1 | Evaluation of data / data quality
1.2.2 | Conceptualisation of a data base
1.2.3 | Construction / Coherence test of the data base
WP 2 | Construction of indicators and risk assessement
2.1 | Determination of spatiotemporal indicators
2.2 | Construction of models of indicators
2.2.1 | Evaluation and validation of models
WP3 | Development of an automated computer system
3.1 | Choise of computer architecture
3.1.1 | Informatic development
3.2 | Implementation / Test
3.2.1 | Webmapping => Online version of the compter system
WP4 | Training
4.1 | Training Doctoral School
4.2 | Other training
WP5 | Dissemination
5.1 | Workshops
5.2 | Conferences
5.3 | Publications
5.4 | Redaction of the thesis
Legend | Collaboration
Team AIMS
TEAM SIC (knowledge and information system)
Team AIMS/SIC
Milestones:
MS1 | First publication
MS2 | Coherent data base
MS3 | Models of indicators
MS4 | Functional automated computer system
MS5 | Second publication

## Feuil3
Work Plan |  | Calendrier
|  | Février | Mars | Avril | Mai | Juin | Juillet
Partie 1 | Approbiation du sujet
1.1 | Bibliographie
1.2 | Définition facteurs de risque
Partie 2 | Chaîne de traitements
2.1 | Conceptualisation des chaînes de traitements
2.2 | Développement informatique
Partie 3 | Développement de l'outil générique
3.1 | Développement informatique